## user stories
name | feature | epic | product_areas | release | sprint | team | owner | story_points | phase
As a mobile user, when I tap the Advantage Home logo, I am redirected to the Home page | Mobile Navigation | Advantage Shopping Mobile | 01 Home Banner | AOS 1.5 |  |  | tom_demo@nga | 2 | New
As a mobile user, when I tap the Search icon, I can enter text successfully into the field | Mobile Navigation | Advantage Shopping Mobile | 01 Home Banner | AOS 1.0 | Sprint 1 | AOS API | cecil_demo@nga | 2 | Done
As a responsive web user, when I click the Person icon, I am prompted to login with my credentials | User Profile | Advantage Shopping Web | 01 Home Banner | AOS 1.5 | Sprint 2 | AOS Infra | mary_demo@nga | 2 | In Testing
As a responsive web user, when I click the Search icon, I can enter text successfully into the field | Navigation | Advantage Shopping Web | 01 Home Banner | AOS 1.5 | Sprint 1 | AOS API | cecil_demo@nga | 3 | Done
As a user, I can define a site theme | Customer Support | Customer Asks | 01 Home Banner | AOS 1.0 | Sprint 3 | AOS UI | kelly_demo@nga | 2 | New
As a responsive web user, when I click Tablets from the Home page, I am taken to the Tablets category page | Navigation | Advantage Shopping Web | 01 Home Banner/Page Jumps,03 Tablets | AOS 1.5 | Sprint 2 | AOS API | michael_demo@nga | 2 | In Progress
As a mobile user, when I tap Special Offer from the Home Banner, I am auto scrolled to the Special Offer | Mobile Navigation | Advantage Shopping Mobile | 01 Home Banner,07 Special Offer | AOS 1.0 | Sprint 2 | AOS API | james_demo@nga | 12 | In Testing
As a responsive web user, when I click Special Offer from the Home Banner, I am auto scrolled to the Special Offer | Navigation | Advantage Shopping Web | 01 Home Banner/Page Jumps,07 Special Offer | AOS 1.0 | Sprint 2 | AOS API | tom_demo@nga | 4 | New
As a mobile user, when I tap Popular Items from the Home page, I am auto scrolled to Popular Item | Mobile Navigation | Advantage Shopping Mobile | 01 Home Banner,09 Popular Items | AOS 1.0 | Sprint 1 | AOS Infra | robert_demo@nga | 3 | Done
As a user, I can set a favorites view for products I like | Customer Support | Customer Asks | 01 Home Banner,11 User Profile | AOS 1.5 | Sprint 3 |  | cecil_demo@nga | 2 | Done
As a mobile user, I can tap the Checkout button and am asked to login | Mobile Checkout | Advantage Shopping Mobile | 01 Home Banner,11 User Profile/Facebook Sign In | AOS 1.0 | Sprint 2 | AOS Infra | mary_demo@nga | 2 | New
As a mobile user, when I tap Person icon, I am prompted to login with my credentials | Mobile User Profile | Advantage Shopping Mobile | 01 Home Banner,11 User Profile/Facebook Sign In | AOS 1.5 |  |  | alice_demo@nga | 6 | New
As a responsive web user, I can click the Checkout button and am asked to login | Checkout | Advantage Shopping Web | 01 Home Banner,11 User Profile/Facebook Sign In | AOS 1.0 | Sprint 1 | AOS UI | alex_demo@nga | 6 | Done
As a responsive web user, I can click the 'Checkout' button from anywhere on the site | Checkout | Advantage Shopping Web | 01 Home Banner,12 Shopping Cart | AOS 1.0 | Sprint 3 | AOS Infra | kelly_demo@nga | 6 | In Progress
As a responsive web user, when I click the Advantage Home logo, I am redirected to the Home page | Navigation | Advantage Shopping Web | 01 Home Banner/Page Jumps | AOS 1.0 | Sprint 2 |  | tom_demo@nga | 2 | Done
As a mobile user, when I tap Speakers from the Home page, I am taken to the Speakers category page | Mobile Navigation | Advantage Shopping Mobile | 02 Speakers, | AOS 1.0 | Sprint 3 | AOS UI | alex_demo@nga | 4 | In Progress
As a responsive web user, when I click Speakers from the Home page, I am taken to the Speakers category page | Navigation | Advantage Shopping Web | 02 Speakers,01 Home Banner/Page Jumps | AOS 1.0 | Sprint 1 | AOS Infra | robert_demo@nga | 6 | Done
As a responsive web user, I can add any Speaker to my cart | Checkout | Advantage Shopping Web | 02 Speakers,12 Shopping Cart | AOS 1.0 | Sprint 1 | AOS Infra | kelly_demo@nga | 6 | Done
As a mobile user, I can add any Speaker to my cart | Mobile Checkout | Advantage Shopping Mobile | 02 Speakers/Roar,02 Speakers/Roar Mini,02 Speakers/Soundlink | AOS 1.0 | Sprint 1 | AOS UI | cecil_demo@nga | 2 | Done
As a mobile user, when I tap Tablets from the Home page, I am taken to the Tablets category page | Mobile Navigation | Advantage Shopping Mobile | 03 Tablets, | AOS 1.5 |  |  | paul_demo@nga | 2 | New
As a responsive web user, I can add any Tablet to my cart | Checkout | Advantage Shopping Web | 03 Tablets,12 Shopping Cart | AOS 1.0 | Sprint 2 | AOS UI | cecil_demo@nga | 4 | New
As a mobile user, I can add any Tablet to my cart | Mobile Checkout | Advantage Shopping Mobile | 03 Tablets/ElitePad,03 Tablets/Elite,03 Tablets/Pro | AOS 1.0 | Sprint 1 | AOS UI | sa@nga | 2 | Done
As a mobile user, when I tap Laptops from the Home page, I am taken to the Laptops category page | Mobile Navigation | Advantage Shopping Mobile | 04 Laptops, | AOS 1.0 | Sprint 2 | AOS API | tom_demo@nga | 6 | In Testing
As a responsive web user, when I click Laptops from the Home page, I am taken to the Laptops category page | Navigation | Advantage Shopping Web | 04 Laptops, | AOS 1.0 | Sprint 1 | AOS UI | alice_demo@nga | 2 | Done
As a responsive web user, I can add any Laptop to my cart | Checkout | Advantage Shopping Web | 04 Laptops,12 Shopping Cart | AOS 1.0 | Sprint 2 | AOS UI | mary_demo@nga | 4 | New
As a mobile user, I can add any Laptop to my cart | Mobile Checkout | Advantage Shopping Mobile | 04 Laptops/Chromebook,04 Laptops/ENVY,04 Laptops/Pavillion,04 Laptops/Spectre,04 Laptops/ZBook | AOS 1.0 | Sprint 3 | AOS API | paul_demo@nga | 2 | New
As a mobile user, when I tap Mice from the Home page, I am taken to the Mice category page | Mobile Navigation | Advantage Shopping Mobile | 05 Mice, | AOS 1.0 | Sprint 2 | AOS UI | alex_demo@nga | 8 | In Progress
As a responsive web user, when I click Mice from the Home page, I am taken to the Mice category page | Navigation | Advantage Shopping Web | 05 Mice, | AOS 1.0 | Sprint 1 | AOS API | tom_demo@nga | 2 | Done
As a responsive web user, I can add any Mouse to my cart | Checkout | Advantage Shopping Web | 05 Mice,12 Shopping Cart | AOS 1.0 | Sprint 3 | AOS UI | cecil_demo@nga | 4 | New
As a mobile user, I can add any Mouse to my cart | Mobile Checkout | Advantage Shopping Mobile | 05 Mice/G502 Proteus,05 Mice/Kensington 72337,05 Mice/Kensington 72352,05 Mice/Optical Mouse,05 Mice/Sculpt Touch,05 Mice/Z3200 Wireless,05 Mice/Z4000 Wireless,05 Mice/Z8000 Wireless | AOS 1.0 | Sprint 1 | AOS UI | paul_demo@nga | 2 | Done
As a mobile user, when I tap Headphones from the Home page, I am taken to the Headphones category page | Mobile Navigation | Advantage Shopping Mobile | 06 Headphones | AOS 1.5 |  |  | paul_demo@nga | 6 | New
As a responsive web user, when I click Headphones from the Home page, I am taken to the Headphones category page | Navigation | Advantage Shopping Web | 06 Headphones | AOS 1.0 | Sprint 3 | AOS API | michael_demo@nga | 2 | In Progress
As a responsive web user, I can add any Headphones to my cart | Checkout | Advantage Shopping Web | 06 Headphones,12 Shopping Cart | AOS 1.0 | Sprint 2 | AOS UI | alice_demo@nga | 4 | New
As a mobile user, I can add any Headphones to my cart | Mobile Checkout | Advantage Shopping Mobile | 06 Headphones/Beats Studio,06 Headphones/HP H2310,06 Headphones/Logitech H390 | AOS 1.0 | Sprint 2 | AOS UI | cecil_demo@nga | 12 | New
As a responsive web user, when I click Popular Items from the Home page, I am auto scrolled to Popular Items | Navigation | Advantage Shopping Web | 09 Popular Items | AOS 1.0 | Sprint 3 | AOS UI | cecil_demo@nga | 4 | New
As a mobile user, I can fill out the in app form to contact support | Mobile Contact Us | Advantage Shopping Mobile | 10 Contact Us | AOS 1.0 | Sprint 3 | AOS Infra | kelly_demo@nga | 6 | In Progress
As a mobile user, I can open a live chat session with customer support | Mobile Contact Us | Advantage Shopping Mobile | 10 Contact Us | AOS 1.0 | Sprint 2 | AOS UI | alex_demo@nga | 4 | In Progress
As a mobile user, I cannot send a message until the required fields are entered | Mobile Contact Us | Advantage Shopping Mobile | 10 Contact Us | AOS 1.0 | Sprint 3 | AOS API | peter_demo@nga | 10 | In Testing
As a responsive web user, I can fill out the in site form to contact support | Contact Us | Advantage Shopping Web | 10 Contact Us | AOS 1.0 | Sprint 1 | AOS UI | alex_demo@nga | 2 | Done
As a responsive web user, I can open a live chat session with customer support | Contact Us | Advantage Shopping Web | 10 Contact Us | AOS 1.0 | Sprint 3 | AOS Infra | paul_demo@nga | 2 | In Progress
As a responsive web user, I cannot send a message until the required fields are entered | Contact Us | Advantage Shopping Web | 10 Contact Us | AOS 1.5 |  |  | kelly_demo@nga | 6 | New
As a user, I can type emojis in the Live Chat | Enhancement Requests | Customer Asks | 10 Contact Us | AOS 1.5 | Sprint 3 |  | cecil_demo@nga | 2 | Done
As a mobile user, I can see an overview of my Account, Shipping, Preferred payment and Notification details | Mobile User Profile | Advantage Shopping Mobile | 11 User Profile | AOS 1.0 | Sprint 2 | AOS Infra | paul_demo@nga | 8 | In Progress
As a responsive web user, I can see an overview of my Account, Shipping, Preferred payment and Notification details | User Profile | Advantage Shopping Web | 11 User Profile | AOS 1.0 | Sprint 1 | AOS API | tom_demo@nga | 2 | Done
As a responsive web user, I can see Product Name, Color, Quantity, Price, and Total | Checkout | Advantage Shopping Web | 11 User Profile | AOS 1.0 | Sprint 2 | AOS API | michael_demo@nga | 2 | In Progress
As a site administrator, I can change the account ownership | User Profile | Advantage Shopping Web | 11 User Profile | AOS 1.5 | Sprint 1 | AOS UI | cecil_demo@nga | 2 | Done
As a mobile user, I can create an account | Mobile User Profile | Advantage Shopping Mobile | 11 User Profile/Create Account | AOS 1.5 |  |  | cecil_demo@nga | 2 | New
As a responsive web user, I can create an account | User Profile | Advantage Shopping Web | 11 User Profile/Create Account | AOS 1.0 | Sprint 3 | AOS Infra | paul_demo@nga | 4 | In Testing
As a mobile user, I can edit my Account, Shipping, Preferred payment and Notification details | Mobile User Profile | Advantage Shopping Mobile | 11 User Profile/Edit Account | AOS 1.5 |  |  | james_demo@nga | 2 | New
As a responsive web user, I can edit my Account, Shipping, Preferred Payment and Notification details | User Profile | Advantage Shopping Web | 11 User Profile/Edit Account | AOS 1.0 | Sprint 2 | AOS UI | alex_demo@nga | 6 | In Progress
As a mobile user, I can login with Facebook | Mobile User Profile | Advantage Shopping Mobile | 11 User Profile/Facebook Sign In | AOS 1.0 | Sprint 1 | AOS Infra | mary_demo@nga | 8 | Done
As a mobile user, I can login with valid user credentials | Mobile User Profile | Advantage Shopping Mobile | 11 User Profile/Facebook Sign In | AOS 1.5 |  |  | james_demo@nga | 2 | New
As a responsive web user, I can login with Facebook | User Profile | Advantage Shopping Web | 11 User Profile/Facebook Sign In | AOS 1.0 | Sprint 3 | AOS API | james_demo@nga | 2 | In Progress
As a responsive web user, I can login with valid user credentials | User Profile | Advantage Shopping Web | 11 User Profile/Facebook Sign In,15 Security/Password | AOS 1.0 | Sprint 3 | AOS UI | alex_demo@nga | 6 | In Progress
As a mobile user, I can edit my cart | Mobile Checkout | Advantage Shopping Mobile | 12 Shopping Cart | AOS 1.0 | Sprint 3 | AOS UI | cecil_demo@nga | 6 | In Progress
As a mobile user, I can remove items from my cart | Mobile Checkout | Advantage Shopping Mobile | 12 Shopping Cart | AOS 1.0 | Sprint 3 | AOS API | michael_demo@nga | 8 | In Testing
As a mobile user, I can see Product Name, Color, Quantity, Price, and Total | Mobile Checkout | Advantage Shopping Mobile | 12 Shopping Cart | AOS 1.0 | Sprint 1 |  | kelly_demo@nga | 6 | Done
As a responsive web user, I can remove items from my cart | Checkout | Advantage Shopping Web | 12 Shopping Cart | AOS 1.0 | Sprint 3 | AOS UI | alex_demo@nga | 2 | In Testing
As a mobile user, I can navigate to my cart by selecting the cart icon | Mobile Checkout | Advantage Shopping Mobile | 12 Shopping Cart,01 Home Banner/Page Jumps | AOS 1.0 | Sprint 1 | AOS Infra | robert_demo@nga | 2 | Done
As a mobile user, I can see my payment options listed below my items | Mobile Checkout | Advantage Shopping Mobile | 13 Payment | AOS 1.0 | Sprint 1 | AOS API | cecil_demo@nga | 2 | Done
As a user, I can choose to receive an invoice of my purchase to my registered e-mail | Invoices | Billing | 13 Payment,11 User Profile | AOS 1.0 | Sprint 2 | AOS UI | cecil_demo@nga | 6 | In Progress
As a user, I can enter my pre-paid gift card pin code to my account | User Profile | Advantage Shopping Web | 13 Payment,11 User Profile | AOS 1.5 |  |  | cecil_demo@nga | 2 | New
As a user, I can purchase pre-paid gift cards | Pre-Paid | Billing | 13 Payment,11 User Profile | AOS 1.5 |  |  | alex_demo@nga | 6 | New
As a user, I can select either Euro or Dollar as the transaction currency | Invoices | Billing | 13 Payment,11 User Profile | AOS 1.5 | Sprint 3 | AOS API | tom_demo@nga | 2 | In Progress
As a user, I want to be able to have a one-click to buy option | Enhancement Requests | Customer Asks | 13 Payment,11 User Profile | AOS 1.5 |  |  | tom_demo@nga | 6 | New
As a user, I can delete a credit card on file | Credit Card | Billing | 13 Payment/Credit Card, 11 User Profile | AOS 1.5 | Sprint 2 | AOS UI | alice_demo@nga | 2 | In Testing
As a user, I can have multiple credit cards on file | Credit Card | Billing | 13 Payment/Credit Card, 11 User Profile | AOS 1.5 | Sprint 3 | AOS Infra | mary_demo@nga | 6 | In Progress
As a user, I can print my invoice after checking out | Invoices | Billing | 13 Payment/Credit Card, 11 User Profile | AOS 1.0 | Sprint 2 | AOS Infra | robert_demo@nga | 2 | In Progress
As a user, I can scan my credit card to enter the information in my profile | Credit Card | Billing | 13 Payment/Credit Card, 11 User Profile | AOS 1.5 |  |  | sa@nga | 5 | New
As a user, I can take a picture of my credit card so that I can save the info in my billing information | Credit Card | Billing | 13 Payment/Credit Card, 11 User Profile | AOS 1.5 | Sprint 1 | AOS API | james_demo@nga | 5 | Done
As a user, when using a credit card on file, I must supply my CCV details | Credit Card | Billing | 13 Payment/Credit Card, 11 User Profile | AOS 1.5 | Sprint 1 | AOS API | michael_demo@nga | 2 | Done
Credit card information is not saved to profile after logging back in - Android | Credit Card | Billing | 13 Payment/Credit Card, 11 User Profile | AOS 1.0 | Sprint 1 | AOS UI | alex_demo@nga | 2 | Done
As a user, I can pay with my PayPal account | PayPal Support | Billing | 13 Payment/PayPal, 11 User Profile | AOS 1.5 | Sprint 1 | AOS Infra | kelly_demo@nga | 8 | Done
As a user, If I do not have a PayPal account, I will be redirected to create a PayPal account | PayPal Support | Billing | 13 Payment/PayPal, 11 User Profile | AOS 1.5 | Sprint 3 | AOS API | peter_demo@nga | 2 | In Progress
As a user, I can only access Advantage Online Shopping over SSL standards | Protocol Downgrade Attack Prevention | Security | 15 Security/Meltdown and Spectre | AOS 1.5 | Sprint 3 | AOS Infra | paul_demo@nga | 8 | In Progress
As a user, I can only access the most recently patched site | Spectre and Meltdown | Security | 15 Security/Meltdown and Spectre | AOS 1.5 | Sprint 3 | AOS Infra | james_demo@nga | 3 | New
As a user, I received an email addressing the Meltdown and Spectre vulnerabilities | Spectre and Meltdown | Security | 15 Security/Meltdown and Spectre | AOS 1.5 | Sprint 2 | AOS Infra | james_demo@nga | 3 | New
As a user, I can login if my password is reactivated by an authorized link | Password Management | Security | 15 Security/Password, | AOS 1.0 | Sprint 2 | AOS UI | alice_demo@nga | 6 | In Progress
As a user, I can login only if I meet the password criteria | Password Management | Security | 15 Security/Password, | AOS 1.5 |  |  | michael_demo@nga | 2 | New
As a user, I can login only if my password is not expired | Password Management | Security | 15 Security/Password, | AOS 1.0 | Sprint 1 | AOS Infra | mary_demo@nga | 2 | Done
As a user, I can request to block my account when account hijacking is suspected | Enhancement Requests | Customer Asks | 15 Security/Password, | AOS 1.0 | Sprint 3 | AOS UI | alex_demo@nga | 4 | In Progress
All communication must be SSL 256 -bit encrypted | Protocol Downgrade Attack Prevention | Security | 15 Security/Secure Login | AOS 1.5 |  |  | robert_demo@nga | 2 | New
As a DDOS hacker, I am known by and stored in the system after 1 incident so that I don’t try it again | DDOS Prevention | Security | 15 Security/Secure Login | AOS 1.0 | Sprint 3 |  | cecil_demo@nga | 2 | New
As a DDOS hacker, I am routed to a mitigation device by in-path deployment | DDOS Prevention | Security | 15 Security/Secure Login | AOS 1.5 |  |  | alex_demo@nga | 4 | New
As a Downgrade Attacker, I am blocked access to the site | Protocol Downgrade Attack Prevention | Security | 15 Security/Secure Login | AOS 1.0 | Sprint 3 | AOS UI | alex_demo@nga | 6 | In Progress
As a user, I am locked out of my account after 5 failed attempts | DDOS Prevention | Security | 15 Security/Secure Login | AOS 1.5 |  |  | robert_demo@nga | 8 | New

## defects
name | feature | epic | product_areas | release | sprint | team | owner | story_points | phase | severity | taxonomies
20+ second response time after clicking Checkout | Checkout | Advantage Shopping Web | 14 Performance/UI Performance | AOS 1.0 | Sprint 2 | AOS UI | alex_demo@nga | 1 | New | Critical | Chrome,MSSQL,Staging
500 Error for all Canadian customers | Customer Support | Customer Asks | 14 Performance/UI Performance | AOS 1.0 | Sprint 3 | AOS Infra | robert_demo@nga | 1 | New | High | IE,Oracle,Production
9+ second login times - KitKat OS on Galaxy S2, LG G Pro Lite, HTC Chacha, Motorola Droid | Mobile Checkout | Advantage Shopping Mobile | 11 User Profile,14 Performance/Database Performance | AOS 1.0 | Sprint 2 | AOS Infra | robert_demo@nga | 1 | New | High | Android,Ubuntu
Activation E-mail sent to Yahoo e-mail address marked as spam | Password Management | Security | 11 User Profile | AOS 1.0 | Sprint 2 | AOS UI | alice_demo@nga | 2 | New | Medium | Dev,WinServer2012
Add money to pre-paid account not working | Pre-Paid | Billing | 11 User Profile,13 Payment | AOS 1.5 |  | AOS API | james_demo@nga | 3 | New | Medium | QA,Staging
Bulk purchase not working with PayPal | PayPal Support | Billing | 13 Payment/PayPal | AOS 1.0 | Sprint 2 |  | mary_demo@nga | 3 | New | Low | Chrome,Dev
Bulk purchase slowly lagging until error thrown | Checkout | Advantage Shopping Web | 13 Payment/Credit Card,14 Performance | AOS 1.0 | Sprint 2 |  |  | 7 | New | Critical | IE,MSSQL,QA
Cannot change password in Chrome | Password Management | Security | 15 Security/Password | AOS 1.0 | Sprint 3 | AOS UI | alex_demo@nga | 3 | New | High | Chrome,QA
Cannot edit my cart in Edge Browser | Checkout | Advantage Shopping Web | 12 Shopping Cart | AOS 1.0 | Sprint 2 | AOS UI | alex_demo@nga | 3 | New | Medium | Chrome,QA
Cannot remove any items from cart on iOS 11.2 | Mobile Checkout | Advantage Shopping Mobile | 12 Shopping Cart | AOS 1.0 | Sprint 3 | AOS UI | cecil_demo@nga | 3 | New | Medium | Dev,MSSQL
Cannot use emojis when mobile chatting with support | Mobile Contact Us | Advantage Shopping Mobile | 10 Contact Us | AOS 1.0 | Sprint 2 | AOS Infra | kelly_demo@nga | 5 | New | Low | Chrome,MSSQL,Staging
Cart icon redirects me to homepage when clicked from Mice category page | Checkout | Advantage Shopping Web | 01 Home Banner/Page Jumps,12 Shopping Cart | AOS 1.0 | Sprint 1 |  |  | 3 | Closed | Low | IE,Oracle,Production
Create account is failed when using special char in the name field | User Profile | Advantage Shopping Web | 11 User Profile/Create Account | AOS 1.0 | Sprint 1 | AOS UI | alex_demo@nga | 2 | Fixed | Low | Android,Ubuntu
Duplicate items added to cart when quantity 1 selected | Mobile Checkout | Advantage Shopping Mobile | 12 Shopping Cart | AOS 1.5 |  | AOS API | michael_demo@nga | 5 | New | Low | Dev,WinServer2012
Help page is not open properly via F1 | Checkout | Advantage Shopping Web | 01 Home Banner | AOS 1.0 | Sprint 2 |  |  | 3 | New | Low | QA,Staging
High-quality mode of operation bypassed on Chrome | Protocol Downgrade Attack Prevention | Security | 15 Security/Meltdown and Spectre | AOS 1.0 | Sprint 2 | AOS API | peter_demo@nga | 3 | New | Low | Chrome,Dev
Invoice downloaded to an android device take long time to open (over 3 seconds to launch) | Invoices | Billing | 14 Performance/UI Performance | AOS 1.0 | Sprint 2 |  | cecil_demo@nga | 3 | New | Low | IE,MSSQL,QA
Invoice sent to Yahoo Emails marked as spam | Invoices | Billing | 11 User Profile | AOS 1.0 | Sprint 3 |  | robert_demo@nga | 3 | New | Low | Chrome,QA
Long login time on IE8 - 23 seconds | User Profile | Advantage Shopping Web | 11 User Profile/Facebook Sign In,14 Performance | AOS 1.0 | Sprint 3 | AOS API | james_demo@nga | 1 | New | Low | Chrome,QA
MasterCard transactions are failing in cards starting with digits 4580 | Credit Card | Billing | 13 Payment/Credit Card | AOS 1.0 | Sprint 1 |  |  | 3 | Closed | Low | Dev,MSSQL
Mobile chat session disconnected after first message is sent | Mobile Contact Us | Advantage Shopping Mobile | 10 Contact Us | AOS 1.0 | Sprint 2 | AOS UI | alex_demo@nga | 3 | Opened | Low | Chrome,MSSQL,Staging
Nothing happens when I tap “Our Products” from the Home screen | Mobile Navigation | Advantage Shopping Mobile | 01 Home Banner/Page Jumps | AOS 1.0 | Sprint 2 | AOS UI | alex_demo@nga | 3 | Opened | Low | IE,Oracle,Production
PayPal redirection link broken | PayPal Support | Billing | 13 Payment/PayPal | AOS 1.0 | Sprint 1 |  | cecil_demo@nga | 3 | Fixed | Low | Android,Ubuntu
PayPal verification Error | PayPal Support | Billing | 13 Payment/PayPal | AOS 1.0 | Sprint 3 | AOS Infra | kelly_demo@nga | 1 | New | Low | Dev,
Search by date returns NULL results | Invoices | Billing | 11 User Profile | AOS 1.0 | Sprint 2 |  |  | 3 | Opened | Low | QA,Staging
Session timeout is 60 min instead of 20 min | Navigation | Advantage Shopping Web | 14 Performance/Database Performance | AOS 1.5 |  | AOS UI | alice_demo@nga | 3 | New | Low | Chrome,Dev
Shopping cart content is not kept when logging out and logging in again | Checkout | Advantage Shopping Web | 12 Shopping Cart,14 Performance/Database Performance | AOS 1.0 | Sprint 1 | AOS Infra | robert_demo@nga | 1 | Fixed | Low | IE,MSSQL,QA
Slow performance when scrolling on a large list of Cart items | Checkout | Advantage Shopping Web | 12 Shopping Cart,14 Performance/UI Performance | AOS 1.0 | Sprint 1 | AOS Infra | kelly_demo@nga | 1 | Fixed | Low | Chrome,QA
Slow response times when accessing from Frankfurt region | Navigation | Advantage Shopping Web | 14 Performance | AOS 1.0 | Sprint 1 | AOS API | michael_demo@nga | 3 | Fixed | Low | Chrome,QA
Tablet view sizing issues | Customer Support | Customer Asks |  | AOS 1.0 | Sprint 2 | AOS UI | cecil_demo@nga | 6 | Opened | Low | Dev,MSSQL
Taken to Special Offer instead of Popular Items when I tap Popular Items | Mobile Navigation | Advantage Shopping Mobile | 07 Special Offer,09 Popular Items | AOS 1.0 | Sprint 2 | AOS Infra | paul_demo@nga | 3 | Fixed | Low | Chrome,MSSQL,Staging
Unable to delete a credit card on file | Credit Card | Billing | 13 Payment/Credit Card | AOS 1.0 | Sprint 1 |  |  | 7 | Closed | Medium | IE,Oracle,Production
Unable to enter pin code | Pre-Paid | Billing | 13 Payment | AOS 1.5 |  | AOS UI | alex_demo@nga | 3 | New | Medium | Android,Ubuntu
Unable to sign in via Facebook, even though user is prompted of successfully login | User Profile | Advantage Shopping Web | 11 User Profile/Facebook Sign In | AOS 1.0 | Sprint 2 | AOS Infra | mary_demo@nga | 1 | Fixed | Medium | Dev,
User can login with both old password and newly created password | Password Management | Security | 11 User Profile,15 Security/Password | AOS 1.0 | Sprint 1 | AOS API | michael_demo@nga | 2 | Fixed | Medium | QA,Staging
Users in Germany did not receive email on Meltdown and Spectre vulnerabilities | Spectre and Meltdown | Security | 15 Security/Meltdown and Spectre | AOS 1.0 | Sprint 2 | AOS Infra | mary_demo@nga | 2 | New | Medium | Chrome,Dev
Web chat pop-up is blocked in Chrome by default | Contact Us | Advantage Shopping Web | 10 Contact Us | AOS 1.5 |  | AOS UI | alex_demo@nga | 2 | New | Medium | IE,MSSQL,QA
Web chat session disconnected after first message is sent | Contact Us | Advantage Shopping Web | 10 Contact Us | AOS 1.5 |  | AOS Infra | paul_demo@nga | 3 | New | Medium | Chrome,QA
When removing a single item from cart, all items are removed | Checkout | Advantage Shopping Web | 12 Shopping Cart | AOS 1.0 | Sprint 2 | AOS API | michael_demo@nga | 2 | Opened | Medium | Chrome,QA
Wrong image is displayed for Mice on the Home page | Navigation | Advantage Shopping Web | 05 Mice | AOS 1.0 | Sprint 1 | AOS UI | alice_demo@nga | 3 | Fixed | Medium | Dev,MSSQL
Credit card information is not saved to profile after logging back in - Android | Credit Card | Billing | 13 Payment/Credit Card,11 User Profile | AOS 1.0 | Sprint 1 | AOS UI | alex_demo@nga | 2 | Closed | Medium | Chrome,MSSQL,Staging

## quality stories
name | product_areas | release | sprint | team | owner | story_points | phase
As a DB Admin, I can modify existing records | 13 Payment,14 Performance/Database Performance,15 Security | AOS 1.0 | Sprint 2 | AOS Infra | cecil_demo@nga | 2 | New
As a DB Admin, I have the privilege to execute stored procedure | 13 Payment,14 Performance/Database Performance,15 Security | AOS 1.0 | Sprint 2 | AOS Infra | cecil_demo@nga | 5 | New
As a Sys Admin, I can ensure we meet compliance | 13 Payment,14 Performance/Database Performance,15 Security | AOS 1.0 | Sprint 2 | AOS Infra | tom_demo@nga | 6 | New